## Sheet1
Day 1: Project Setup and Planning
Area | Tasks
PRD | Define problem statement, target users, MVP scope, user journey, success metrics | done
GitHub | Create repo, add branch strategy, folder structure, README, .gitignore | done
Environment | Setup .env files, Python venvs, React dependencies, Docker PostgreSQL | done
Architecture | Finalize frontend, backend, AI orchestration, database, RAG, and deployment structure | done
Backend Skeleton | Create FastAPI app, health check endpoint, database connection | done
Frontend Skeleton | Create React app pages: login, signup, dashboard, upload, reports | done
Deliverable | Repo initialized, local app runs, database runs, setup documented | done
Day 2: UI and Backend Integration
Area | Tasks
Auth UI | Login/signup forms, validation, error messages, CORS fix | done
Backend APIs | Auth, user profile, upload, meal/report, history endpoints | done
Database | Create tables, relationships, basic CRUD operations | done
UI Integration | Connect React frontend to FastAPI APIs using env API URL | done
Error Handling | Add loading states, empty states, backend validation messages | done
Manual Testing | Test signup, login, profile save, upload, report fetch | done
Deliverable | Frontend and backend connected end to end | done
Day 3: RAG, Evaluation, Observability, Stress Test Strategy
Area | Tasks
RAG Upload | Build upload page and backend upload endpoint
Document Processing | Extract text, clean content, chunk documents, store metadata
Retrieval | Implement embeddings, vector store/search, top-k retrieval
Generation | Build RAG prompt, call LLM, return answer with sources
Evaluation | Create test questions, expected answers, relevance checks, hallucination checks
Observability | Add logs, request IDs, health checks, error tracking plan, latency tracking
Stress Testing | Define scenarios: concurrent users, large files, slow LLM, DB load, timeout, retry
Deliverable | RAG MVP works and has evaluation/monitoring/stress-test strategy
Day 4: GitHub Actions, Azure AI RAG, Deployment Setup
Area | Tasks
GitHub Actions | Add CI for backend syntax/tests and frontend build
Azure AI | Integrate Azure OpenAI or Azure AI Foundry for model calls
Azure RAG | Connect Azure AI Search/vector index and Blob Storage for documents
Secrets | Configure GitHub secrets and Azure env variables
Deployment Infra | Prepare Dockerfiles, Docker Compose, deployment config
Production Config | Configure production CORS, database URL, API URLs, model keys
Testing | Run CI, backend checks, frontend build, Azure RAG smoke test
Deliverable | CI pipeline and Azure AI RAG integration ready for deployment
Day 5: Deployment, Final Testing, Documentation
Area | Tasks
Deployment | Deploy frontend, backend, AI orchestrator, database, and RAG services
End-to-End Testing | Test signup to upload to RAG answer/report on deployed app
RAG Evaluation | Run evaluation dataset and record results
Stress Test | Run small load test and document bottlenecks
Observability | Verify logs, health checks, error visibility, latency tracking
Documentation | Final README, architecture diagram, setup guide, API docs, screenshots
Submission | Push final code, submit GitHub repo, deployment link, docs, evaluation report
Deliverable | Project is live, tested, documented, and ready for review
Quick Milestones
Day | Milestone
Day 1 | Project is created and runnable locally
Day 2 | UI talks to backend and database
Day 3 | RAG works with evaluation and test strategy
Day 4 | Azure AI + GitHub Actions + deployment setup ready
Day 5 | Final deployed project submitted